## Sheet1
Story | Task Number | Task | Work Hours | Points
Story 3 | a. | Set up database for storing all information related to a boarding appointment. | 4 | 1
| b. | Create database fields to contain and retrieve information on the dogs being boarded, their owners (with contact information) and any special concerns or issues for the dogs. | 8 | 2
| c. | Create inputs on the website for the customer to enter and add information about and related to their dog(s) and the appointment, which information will be stored in the database | 4 | 1
| d. | Create links between the database, website calendar and appointment scheduler. | 2 | 1
| e. | Create visual layout for section of website dedicated to boarding. | 16 | 3
Total Points |  |  |  | 8
Story 1 | a. | Create visual layout for calendar on website. | 16 | 3
| b. | Set up calendar program being used for website calendar. | 8 | 3
| c. | Set up database to use for calendar. | 4 | 1
| d. | Set up database fields to store appointment dates and times and the people reserving them. | 8 | 2
| e. | Link calendar database with calendar interface. | 2 | 1
Total Points |  |  |  | 10